## Sheet1
ID | feature | verification objective(what) | how | coverage plan | assumptions/dependencies | where | status | notes
obj 001 | Lock Acquisition (Frame Alignment Detection) | Verify frame_detect rises to 1 right after the 3rd consecutive valid frame, not earlier and not later | Drive 3+ back-to-back valid frames (HEAD1/HEAD2, payload 10). The scoreboard compares frame_detect to the reference model on every clock | cg_events.cp_fd_edge bin acquire (0→1); cg_bus.cp_frame_detect (both values) | Continuous input stream with no idle gaps. A frame is 12 bytes. Headers are 0xAFAA / 0xBA55 | test: frame_lock_test, frame_spec_test + scoreboard | success | frame_detect rises after the 3rd valid frame on the same clock as the reference model, with 0 mismatches.
obj 002 | Byte Position Counter Range | Verify fr_byte_position never exceeds 11, and while aligned it counts 0→11 and wraps back to 0 at the frame boundary | SVA a_max_byte_pos in interface.sv (fr_byte_position <= 11), checked on every clock in every test. The scoreboard compares fr_byte_position to the reference model on every clock | cg_bus.cp_byte_pos: 12 bins (0–11), illegal_bins for 12–15; cg_bus.cp_pos_wrap: wrap_11_to_0, step_0_to_1, hold_0_to_0 | A frame is 12 bytes (2 header + 10 payload). Position 0 is the header LSB | interface: a_max_byte_pos (all tests) + scoreboard | success | The assertion passes in every run.
obj 003 | Dual Header Pattern Support (HEAD1 / HEAD2) | Verify the block locks on both header patterns (0xAFAA, 0xBA55), each on its own and mixed | Send alternating HEAD1/HEAD2 frames during lock acquisition and one frame after lock. HEAD1-only and HEAD2-only lock come from frame_lock_test and frame_spec_test. The scoreboard compares frame_detect and fr_byte_position | cg_bus.cp_rx_class (all 4 header bytes); cg_bus.x_hdr_byte_vs_pos (header byte at position 0/1) | A mix of patterns is allowed for acquiring lock. The spec says "the correct header pattern", so this is an open question for the spec owner (D4) | test: frame_mixed_hdr_test, frame_lock_test (HEAD1 only), frame_spec_test (HEAD2 after re-lock) + scoreboard | success | The block locks on HEAD1 only, HEAD2 only, and a mix.
obj 004 | Illegal Header Handling | Verify that one illegal header in the lock-acquisition sequence resets the count: after 2 valid frames and 1 illegal one, frame_detect does not rise, and 3 more valid frames are needed to lock | Send 2 valid frames, then an illegal header, then valid frames. The scoreboard checks that frame_detect rises only after the 3rd valid frame after the illegal one | cg_events.cp_fd_edge bin acquire; cg_bus.cp_rx_class (RX_OTHER at the header position) | The 3 frames must be consecutive. | test: frame_payload_hdr_ok_test, frame_unlock_test + scoreboard | success | Tested: an illegal header before any valid frame (frame_payload_hdr_ok_test) and while aligned (frame_unlock_test, frame_payload_hdr_ok_test) - frame_detect never rose early.
obj 005 | Partial Header Fault Detection (Valid LSB, Invalid MSB) | Verify that a valid LSB (AA/55) followed by a byte that is neither the matching MSB nor another LSB returns the block to searching: fr_byte_position stays 0, and frame_detect does not change | Send 6 frames with a mixed header (AA BA / 55 AF), then 4 clean frames. The scoreboard compares fr_byte_position and frame_detect on every clock | cg_pattern.cp_pattern (the LSB + wrong-MSB pattern); cg_bus.cp_pos_wrap bin hold_0_to_0 | Waveform 2 overrides the state diagram: while searching, position stays 0. The case where the second byte is a valid LSB is in obj 006 | test: frame_cross_hdr_test + scoreboard | FAIL | fr_byte_position shows 1 for one clock instead of staying 0. After the clean frames it locks normally. This contradicts the spec itself (waveform 2 vs. the diagram), and waveform 2 was chosen. (Bug 3)
obj 006 | LSB, LSB, MSB (valid LSB in place of the MSB) | Verify that a valid LSB in place of the MSB is checked again as a new LSB, so a valid header that starts one byte later is detected (AA AA AF, AA 55 BA, 55 AA AF) | Send AA AA AF + 9 payload bytes repeated (a legal header every 12 bytes) while aligned, not aligned, and acquiring. Control: AA AA AA AF. Cross patterns: AA 55 BA and 55 AA AF. The scoreboard compares frame_detect and fr_byte_position | cg_pattern.x_pattern_vs_lock (PAT_LSB_LSB_MSB, PAT_CROSS_RETEST × frame_detect) | Frames are 12 bytes and arrive back-to-back. The extra LSB byte is the last byte before the header, not a separate byte added to the stream. The FSM in the spec is incorrect. | test: frame_lsb_lsb_msb_test; control: frame_lsb_lsb_lsb_msb_test; frame_cross_retest_test (+swap=1 for 55 AA AF) + scoreboard | FAIL | While not aligned, the reference model locks on AA AA AF, but the DUT frame_detect stays 0 and fr_byte_position does not follow the header. AA 55 BA and 55 AA AF fail the same way (the DUT never locks, the model locks after 3 frames). Control: with AA AA AA AF the DUT does lock and frame_detect matches the reference model, so only the second byte is not checked again. The control run still shows 1 fr_byte_position error, on the first frame only: on the second AA the DUT shows position 1 instead of 0.(Bug 2)
obj 007 | Continuous Back-to-Back Frame Streaming | Verify frame_detect stays 1 and fr_byte_position keeps counting correctly over a long run of valid frames with no gaps | Lock, then send consecutive valid frames (payload with no AA/55). The scoreboard compares frame_detect and fr_byte_position on every clock | cg_bus.cp_frame_detect bin locked; cg_bus.cp_pos_wrap bin wrap_11_to_0 | Payload does not contain AA/55, so it does not trigger bug 1. | test: frame_lock_test + scoreboard | success | A long run of consecutive valid frames was performed. frame_detect stays 1 with 0 mismatches and no false unlock. legal_frame_counter wraps every 4 frames with no effect on the outputs
obj 008 | Payload Transparency / False Header in Payload | Verify header values inside the payload (AA AF / 55 BA), at any position including a single AA/55 on the last byte right before the next header, do not change alignment. While frame_detect = 1, the block keeps the 12-byte grid. While frame_detect = 0, there is no false lock | Lock with 4 good frames, then 10 frames with a bad header and a planted value in the payload, location chosen cyclically 0–9 (0–8: AA AF pair, 9: single AA before the next header), each followed by 6 good frames. Controls: no planted value, and the same planted value while not aligned. The scoreboard compares frame_detect and fr_byte_position | cg_bus.x_hdr_byte_while_locked (header byte × frame_detect); cg_bus.x_hdr_byte_vs_pos (header byte × position) | While frame_detect = 1, a header is checked only at the frame boundary. The payload can contain any value | test: frame_false_lock_test (cyclic location 0–9); control: frame_payload_hdr_ok_test + scoreboard | FAIL | While aligned, the DUT re aligns on the header value inside the payload: with the planted pair inside the payload fr_byte_position counts 1, 2, 3… from the planted pair while the reference model is at 0. frame_detect stays 1 during the misalignment, so there is no indication. The error appears at all 10 planted positions .
obj 009 | Alignment Recovery After Partial Loss Count | Verify that when bad frames arrive while aligned, but fewer than 48 bytes, the block stays aligned and returns to normal frame counting as soon as a valid frame arrives: frame_detect stays 1, and fr_byte_position continues on the original grid | Lock with 4 valid frames, send 1 bad frame (payload without AA/55), then 4 valid frames. Repeat for both bad header types. The scoreboard compares frame_detect and fr_byte_position on every clock | cg_bus.cp_frame_detect bin locked; cg_bus.cp_pos_wrap bin wrap_11_to_0 | Fewer than 48 bad bytes do not release the lock. A valid header at the frame boundary restarts the loss count | test: frame_payload_hdr_ok_test + scoreboard | success | After one bad frame, frame_detect stays 1, and the following valid frames keep the grid, with 0 mismatches.
obj 010 | Loss of Lock (Out-of-Frame Declaration) | Verify frame_detect drops to 0 after 48 consecutive bytes with no valid header, on the same clock as the reference model, not earlier and not later | Lock with valid frames, then send 4 illegal frames (48 bytes) whose first byte is not AA/55, so no LSB candidate is created. The scoreboard compares frame_detect on every clock | cg_events.cp_fd_edge bin lose (1→0) | The loss threshold is 48 bytes. The count starts from the last valid header | test: frame_unlock_test, frame_spec_test + scoreboard | success | 4 illegal frames = 48 bytes. frame_detect drops exactly on the last byte, with 0 mismatches. Internally na_byte_counter continues past 47 , which is not visible at the outputs.
obj 011 | Re-Lock Recovery After Loss of Lock | Verify that after losing lock (4 illegal frames = 48 bytes) the block returns to searching and locks again after exactly 3 valid frames | Lock with 4 valid frames, send 4 illegal frames (48 bytes) until the loss, then 4 valid frames. The scoreboard compares frame_detect and fr_byte_position on every clock | cg_events.cp_fd_edge bins acquire and lose (both edges in the same run) | After a loss, the lock-acquisition logic starts from zero with no memory of the previous lock | test: frame_unlock_test, frame_spec_test + scoreboard | success | lock→unlock→lock: frame_detect drops on the 48th byte and rises again after the 3rd valid frame, on the same clocks as the reference model, with 0 mismatches.
obj 012 | Variable-Length Payload (Random) | Verify lock and loss of lock match the reference model under random traffic: payload length 10–40 and payload bytes that include header values | Lock with 4 clean frames, then 50 random frames (+num_frames to change). Payload length 10 at 70% and 11–40 at 30%; payload bytes weighted toward AA/55/AF/BA (5% each). The scoreboard compares frame_detect and fr_byte_position on every clock | cg_events.cp_fd_edge (acquire / lose); cg_pattern.cp_pattern (patterns created by the random stimulus) | Payload lengths 11–40 are outside the spec (a frame is 12 bytes). Results depend on the seed and on num_frames | test: frame_random_test (frame_weighted_random_seq) + scoreboard | informational | Not a pass/fail objective: frames of 13–42 bytes are outside the spec. The reference model locked and lost lock 5 times, while the DUT locked once and never lost lock. This is consistent with bug 1 (obj 008) and is not counted as a separate result
obj 013 | Loss of Lock Corner – Header Completed on the 48th Byte | Verify frame_detect behavior when a valid header (AA AF) is completed exactly on the 48th consecutive non-aligned byte while aligned | Lock with 4 valid frames, send 3 illegal frames , then an illegal frame with AA AF planted at payload[8],[9] (bytes 47,48 of the loss count), then 4 valid frames. The scoreboard compares frame_detect and fr_byte_position on every clock | cg_events.cp_fd_edge bins lose and acquire | While aligned, a header is checked only at the frame boundary, so an off-grid header does not stop the loss count | test: frame_na47_hdr_test + scoreboard | success | frame_detect drops on the 48th byte on the same clock as the reference model (no frame_detect error at the loss). The run still shows 13 position errors and 12 frame_detect errors: the DUT locks on the planted AA AF, misses the next real header, and re-locks one frame later than the model. This is caused by bug 1